## Test Levels
Test Level | Purpose | Responsible | Accountable | Consult | Inform | Test Types | Test Coverage | Inputs | Entry Criteria | Exit Criteria
Smoketest | To verify a minimal set of key functionality, designed to determine whether there are any basic problems that will prevent the progression into full scale System test. (i.e. installed the new software, configured it - set up users and roles - make sure that basic functionality works, ie log-in, going to a search screen etc) | ▪Test Lead | ▪IT ▪Systems Architect | ▪Technical Authority ▪Project Management ▪Business Users | ▪Test Engineers | ▪Functional testing; | ▪System Requirements ▪Customer Requirements | ▪Stakeholder Requirements ▪System Requirements | ▪Test Scripts and Test Data have been created & peer reviewed; ▪A schedule for execution has been agreed; ▪A Test Environment has been made available, updated and verified; | ▪System Test Scripts have been executed as scheduled; ▪Actual Results have been verified against Expected Results; ▪Test Evidence has been recorded as appropriate; ▪Required Test Coverage has been achieved; ▪Any unresolved defects have an agreed plan for resolution or closure; ▪No known defects impact the ability to move to the next Test Level;
System Test | To verify the functionality of the system as a single solution (i.e. test all activities in AP from data entry / viewing / deleting information / creating PO etc) | ▪Test Lead | ▪SMEs | ▪Technical Authority ▪Project Management ▪Business Users | ▪Stakeholders | ▪Requirements-based testing; ▪Functional testing; ▪Compliance testing; ▪Security testing; ▪Usability testing; ▪Negative testing; ▪Regression testing; ▪Performance testing. | ▪System Requirements ▪Customer Requirements | ▪Stakeholder Requirements ▪System Requirements | ▪Smoke Testing Exit Criteria has been successfully met; ▪Test Scripts and Test Data have been created & peer reviewed; ▪A schedule for execution has been agreed; ▪A Test Environment has been made available, updated and verified; | ▪System Test Scripts have been executed as scheduled; ▪Actual Results have been verified against Expected Results; ▪Test Evidence has been recorded as appropriate; ▪Required Test Coverage has been achieved; ▪Any unresolved defects have an agreed plan for resolution or closure; ▪No known defects impact the ability to move to the next Test Level;
Delivery Acceptance Test | To confirm the quality of external deliveries before significant time and effort is spent on further testing (i.e. a third party's file which is relied upon for validation; is the file in the expected format and data can be read from it) | ▪Test Lead | ▪SMEs | ▪Technical Authority ▪Project Management ▪Business Users | ▪Stakeholders | ▪Requirements-based testing; ▪Functional testing; ▪Compliance testing; ▪Usability testing; ▪Negative testing; ▪Regression testing. | ▪Partial Customer and System Requirements | ▪SoW with Vendor | ▪Test Scripts and Test Data have been created and peer reviewed; ▪A schedule for execution has been agreed; ▪A Test Environment has been made available, updated and verified; | ▪Test Scripts have been executed as scheduled; ▪Actual Results have been verified against Expected Results; ▪Test Evidence has been recorded as appropriate; ▪Required Test Coverage has been achieved; ▪Any unresolved defects have an agreed plan for resolution or closure; ▪No known defects impact the ability to move to the next Test Level(s).
Data Migration Test | To ensure that process and operations to extract, clean, transform (re-format) and load data from an existing system’s database to a new system’s database can be conducted correctly when the changeover takes place; To check the completeness of migrated data To verify that old and new data can co-exist on the new system To establish time needed for the Data Migration processes To test the back out and recovery scenarios for data Data Migration To check the Security of the Data Data Migration process To validate the security of migrated data | ▪Test Lead | ▪Data Migration Lead | ▪Technical Authority ▪Data Migration Specialists ▪Business Users ▪Project Management | ▪Stakeholders | ▪Functional testing; ▪Performance testing; ▪Security testing; ▪Data Integrity testing; ▪Regression testing | ▪Data Migration Requirements | ▪Data Migration Requirements ▪Data Integrity Requirements ▪Data Migration Performance Requirements (i.e. time to execute) | ▪Smoke/System Testing Exit Criteria has been successfully met; ▪Test Scripts and Test Data have been created & peer reviewed; ▪A schedule for execution has been created; ▪A Test Environment has been made available, updated and verified. | ▪Test Scripts have been executed as scheduled; ▪Actual Results have been verified against Expected Results, and Test Evidence recorded as appropriate; ▪Required Test Coverage has been achieved; ▪Any unresolved defects have an agreed plan for resolution or closure; ▪No known defects impact the ability to move to the next Test Level(s).
System Integration Test | To test the interaction of the new or updated IT system with other internal or external IT systems. (i.e. interfaces) | ▪Test Lead | ▪SMEs ▪IT | ▪Technical Authority | ▪Stakeholders | ▪Interface testing; ▪End-to-End Functional testing; ▪Negative testing; ▪Regression testing. | ▪Interface Reuirements ▪System Requirements ▪Technical requirements | ▪System Requirements ▪Interface Requirements | ▪Smoke Testing, System Testing or Delivery Acceptance Testing Exit Criteria has been successfully met; ▪Test Scripts and Test Data have been created and peer reviewed; ▪A schedule for execution has been agreed; ▪A Test Environment has been made available, updated and verified; | ▪System Integration Test Scripts have been executed as scheduled; ▪Actual Results have been verified against Expected Results; ▪Test Evidence has been recorded as appropriate; ▪Required Test Coverage has been achieved; ▪Any unresolved defects have an agreed plan for resolution or closure; ▪No known defects impact the ability to move to the next Test Level;
Operational Acceptance Test | For operational procedural activities to be verified, including anything from scheduling of batch jobs and back-ups to Helpdesk processes and procedures | ▪Test Lead | ▪IT | ▪Technical Authority ▪Support Managers | ▪Stakeholders | ▪Supportability testing; ▪Recovery testing; ▪Regression testing | ▪Operational & Support Requirements | ▪Operational Requirements ▪Support Requirements ▪Target Operating Model Requirements | ▪Data Migration, System Testing and System Integration Testing Exit Criteria have been successfully met; ▪Test Scripts and Test Data have been created and peer reviewed; ▪A schedule for execution of has been created; ▪A Test Environment has been made available, updated and verified. | ▪Operational Acceptance Test Scripts have been executed as scheduled; ▪Actual Results have been verified against Expected Results, and Test Evidence recorded as appropriate; ▪Required Test Coverage has been achieved; ▪Any unresolved defects have an agreed plan for resolution or closure; ▪No known defects impact the ability to move to the next Test Level(s).
User Acceptance Test | This level of testing provides the prospective end users of a new or changed IT system with the opportunity to verify that it meets expectation and provides the benefits expected. | ▪Test Lead | ▪SMEs ▪IT | ▪Technical Authority ▪Business Users ▪External Users | ▪Stakeholders | ▪Business process-based testing; ▪Usability testing; ▪Requirements-based testing; ▪Ad-hoc/Exploratory testing; ▪Regression testing; | ▪User Requirements | ▪Stakeholder Requirements ▪System Requirements | ▪Data Migration, System Testing and System Integration Testing Exit Criteria have been successfully met; ▪Test Scripts and Test Data have been created and reviewed; ▪A schedule for execution has been created; ▪A Test Environment has been made available, updated and verified. | ▪User Acceptance Test Scripts have been executed as scheduled; ▪Actual Results have been verified against Expected Results, and Test Evidence recorded as appropriate; ▪The required level of Test Coverage has been achieved; ▪Any unresolved defects have an agreed plan for resolution or closure; ▪No known defects impact the ability to move to the next Test Level(s).
Deployment Test | To ensure that a new IT system or IT system release is complete and can be implemented without issue or risk of compromising an existing production system (for example software upgrades) | ▪Test Lead | ▪IT | ▪Technical Authority ▪Support Managers ▪Support Staff ▪Technical Specialists | ▪Stakeholders | ▪Installation testing; ▪Rollback testing; ▪Dress Rehearsal testing. | ▪Deployment Process | ▪Operational Requirements ▪Support Requirements ▪Target Operating Definition ▪Risk Management Requirments | ▪User Acceptance Testing has been completed; ▪Operational Acceptance Testing has been completed; ▪A set of Tests for Deployment Testing has been agreed; ▪A schedule for the execution of Deployment Tests has been created; ▪A Test Environment has been made available and verified. | ▪All Deployment Tests have been executed as scheduled; ▪Actual Results have been verified against Expected Results, and Test Evidence recorded as appropriate; ▪The required level of Test Coverage has been achieved; ▪Any unresolved defects have an agreed plan for resolution or closure; ▪No known defects impact the ability to move into release Implementation.
Live Confidence/Post Commissioning Testing | To verify that an implementation has been successful before an IT system is confirmed as available for use by the end users of the system (for example helps the go-live decision) | ▪Test Lead | ▪SMEs ▪IT | ▪Technical Authority ▪Business Users ▪External Users | ▪Stakeholders | ▪Release Implementation testing | ▪Deployment Process | ▪Stakeholder Requirements | ▪All planned Test Levels have been completed, with no outstanding P1 defects. ▪A set of Test Scripts from previous test levels has been agreed for Live Confidence Testing; ▪A schedule for the execution of Test Scripts has been created | ▪All Live Confidence Test Scripts have been executed as scheduled; ▪Actual Results have been verified against Expected Results, and Test Evidence recorded as appropriate; ▪Required Test Coverage has been achieved, as defined within the Test Plan.
Security - Penetration Test | Penetration test simulates an attack by a malicious party. Penetration testing goes beyond vulnerability scanning to use multistep and multivector attack scenarios that first find vulnerabilities and then attempt to exploit them to move deeper into the enterprise infrastructure. Since this is how advanced targeted attacks work, penetration testing provides visibility into aggregations of misconfigurations or vulnerabilities that could lead to an attack that could cause serious business impact. As a minimum, penetration testing provides a means for prioritizing the highest risk vulnerabilities. (i.e. should be provided by the Cloud provider - Oracle) | ▪Test Lead | ▪External Penetration Test Specialists | ▪Technical Authority ▪Cloud Service Provider | ▪Stakeholders | ▪Penetration Test | ▪Security Requirements | ▪System Access Entry Point ▪ Authorisation from Service Provider to commence this Test Level has been granted | ▪All planned Test Levels have been completed, with no outstanding P1 defects. ▪A schedule for the execution of the Test has been created. | ▪All planned Penetration Test activities are completed
Dynamic Application Security Test | Dynamic application security testing (DAST) technologies are designed to detect conditions indicative of a security vulnerability in an application in its running state. Most DAST solutions test only the exposed HTTP and HTML interfaces of Web-enabled applications; however, some solutions are designed specifically for non-Web protocol and data malformation (for example, remote procedure call, Session Initiation Protocol [SIP] and so on) (i.e. should be provided by the Cloud provider - Oracle) | ▪Test Lead | ▪External Penetration Test Specialists | ▪Technical Authority ▪Cloud Service Provider | ▪Stakeholders | ▪Dynamic Application Security Test | ▪Security Requirements | ▪System Access Entry Point ▪ Authorisation from Service Provider to commence this Test Level has been granted | ▪All planned Test Levels have been completed, with no outstanding P1 defects. ▪A schedule for the execution of the Test has been created. | ▪All planned Dynamic Application Security Test activities are completed
Regression Test | Re-running functional and non-functional tests to ensure that previously developed and tested software still performs after a change (rerunning a selection of tests from any test levels to make sure the change hasn't broken anything) | ▪Test Lead | ▪SMEs ▪IT ▪Data Migration Lead